Software Project Management Plan

for

“TSNHS Gateway Monitoring System”

Renan Erl Dacay

Aljoe Anthony Berdin

Joseph Dakoykoy

Maria Lyn Saludes

Mariae May Salpid

Cherrylen Casimero

- List of Figures

Figure 1 External Structure	6

Figure 2 Internal Structure	6

Figure 3 Feature Breakdown Structure	8

- List of Tables

Table 1 Definition, Acronyms, and Abbreviations	4

Table 2 Roles and Responsibilities	7

Table 3 Staff and Person Involved in Project	9

Table 4 Work Plan	11

Table 5 Work Activities	15

Table 6 Methods and Techniques	18

Table 7 Tools	18

Overview

The system focuses on monitoring the students’ ins and outs of the school campus. It would help the monitoring of the students faster and easier with an assurance that it can produce accurate output that has been generated.

  - Project Summary

The Gateway Monitoring System is a new system introduced to TSNHS. A project that is being built with the use of Radio-frequency identification (RFID) card which transmits data to RFID computer system. It also uses Short Message Service (SMS) which sends students’ monthly report to their respective parents. Its main purpose is to monitor the students’ ins and outs of the school campus.

    - Statement of the Problem

The problem that lead the proponents proposed the gateway monitoring system to TSNHS:

- The parents are complaining to their students’ advisers regarding with low grades despite attending classes every day. On their present system, the teacher will scan manually the attendance of the student whom the parent is complaining to. This process will add to the task of the teacher. And the problem there is when several parents complain simultaneously, the teacher will be having a hard time performing manual scanning of the attendance. The teachers cannot perform well on their strategic functions because they will be bogged down in minutiae.

    - Purpose, Scope and Objectives

Purpose

To address the present situation that the TSNHS is dealing with. The proposed system will automate the manual scanning of students’ attendances to lessen the workload of the respective teacher so that they can save more time and energy to be used in performing strategic function as a teacher.

Scope

The proposed project is intended only for Tagum Sur National High School. The Tagum Sur National High School, parents, and students can benefit the better services in terms of monitoring and keeping track of the students’ ins and outs of the school campus.

The TSNHS Gateway Monitoring System provides the following features:

ADMIN

- Dashboard: is a visual display of all the students entered the campus.

- Students: shows the details of all the students.

- Grade and Section: designated grade and section of the students

- Teachers: shows the details of all the teachers.

- Advisory: specific grade and section designated

- Daily Record: shows student’s daily record

- Monthly Record: shows student’s monthly record

- Users: display all users

ADVISER

- Students: display all students belong in this adviser

- Monthly Record: shows student’s monthly record

STUDENT

- RFID_StudentData (Student View): displays the data of the students after they scan RFID card to RFID reader.

Objectives

The objectives of the proposed system are the following:

- To help out parents and teachers in monitoring their students.

- To lessen the workload of the teachers.

- To modernize students monitoring in TSNHS.

    - Assumptions and Constraints

The Client-server configuration of the TSNHS Gateway Monitoring System is intended.

- Framework:				Laravel

- Back-end:				Hypertext Preprocessor

- Front-end:				Bootstrap Framework

- Coding Pattern:			MVC Architecture

- Database Server:			MySQL

- Web Server:				Apache

This project is set to finish on April 3, 2023 and subject for testing afterwards.

    - Project Deliverables

All of the items listed in this subsection are the deliverables that are to be provided prior to completion of the project.

- Software Documentation (Software Engineering Docs)

- Software Project Management Plan (SPMP)

- Software Requirements Specification (SRS)

- Software Design Documentation (SDD)

- Software Test Documentation (STD)

- Software Program (TSNHS Gateway Monitoring System)

- Installation of software program on target hardware

- Instructional materials need for the orientation of affected users.

  - Evolution of Plan

The Project Manager must first approve all modifications to the project management plan before they can be carried out. In order to keep the project management plan accurate and current, all modification should be documented.

  - Definition, Acronyms, and Abbreviations

| Terms | Definition |
| --- | --- |
| TSNHS | Tagum Sur National High School |
| Laravel | Laravel is a free and open-source PHP web framework, created by Taylor Otwell and intended for the development of web applications following the model–view–controller architectural pattern and based on Symfony. |
| LAN | Local Area Network. A computer network that links devices within a building or group of adjacent buildings. |

Table 1 Definition, Acronyms, and Abbreviations

  - References

- Jinushia R., S. Senthilkumar, S. Bhuvaneswari and E. Clapton, "Smart Monitoring System using RFID Technology," 2020 6th International Conference on Advanced Computing and Communication Systems (ICACCS), 2020, pp. 1430-1433, doi: 10.1109/ICACCS48705.2020.9074448.

- Ravishankar Yadav, Sumita Nainan, 2014, Design of RFID Based Student Attendance System with Notification to Parents Using GSM, INTERNATIONAL JOURNAL OF ENGINEERING RESEARCH & TECHNOLOGY (IJERT) Volume 03, Issue 02 (February 2014).

- M. Kassim, H. Mazlan, N. Zaini, M.K. Salleh. Web-based student attendance system using RFID technology. IEEE Control and System Graduate Research Colloquium, 7 MATEC Web of Conferences 164, 01020 (2018) https://doi.org/10.1051/matecconf/201816401020 ICESTI 2017 (Selangor, Malaysia, 2012). ICSGRC:213-218(2012)

- Longe O.O.(2009),”Implementation of Student Attendance System using RFID Technology”, B. Tech Project Report, Ladoke Akintola University of Technology, Ogbomoso, Nigeria.

- Mohd  Firdaus  Bin  Mahyidin  (2008).  Students’  attendance  system  using  RFID  technology. Malaysia.

- Mc’ Oswel Jamin  Sibin  (2010). RFID  Based  Attendance  System.   University  of  Technology Malaysia: Degree Thesis.

- Project Organization

  - External Structure

Created for Tagum Sur National High School is the TSNHS Gateway Monitoring System. The admin and advisers with all make use of it. Below is a presentation of it. The organizational chart for the exterior structure. Inside organizational.

Figure 1 External Structure

  - Internal Structure

The TSNHS Gateway Monitoring System project is made of a male and female development team, which includes a Project Manager, Team Lead, Agile DBA, Developer, Software Tester, Front End Designer, and Researcher. Figure 2 shows the communication and authority channels between the aforementioned units.

Figure 2 Internal Structure

  - Roles and Responsibilities

This section of the document describes the role and responsibilities for each member in an agile team that will be involve in project to deliver TSNHS Gateway Monitoring System software requirements.

| ROLE | RESPONSIBILITIES |
| --- | --- |
| Project Manager | Monitor product backlog, User acceptance test and sign off |
| Developer | Source code management, Code review and integration, Unit test |
| UI/UX Design | Source code of front-end design |
| Lead Tester | Test case management, Test case script review |
| Tester | Test case script execution |

Table 2 Roles and Responsibilities

- Managerial Process Plans

  - Start-up Plan

    - Estimation Plan

Due to the changing nature of user-defined requirements, the proponent will employ agile software development. It is certain that restrictions and regulations will change throughout the project's development and even after it has been deployed. Three iterations of the development will be made, however if more modifications are made after these iterations, the development may expand.

Figure 3 Feature Breakdown Structure

3.1.2. Staffing Plan

The table below shows the team member involved in TSNHS Gateway Monitoring System Project.

| Name | Position | Status |
| --- | --- | --- |
| School Principal | Product Owner | Full Time |
| Renan Erl E. Dacay | Project Manager | Full Time |
| Aljoe Anthony V. Berdin | Developer | Full Time |
| Joseph Dakoykoy | UI Design | Full Time |
| Maria Lyn Saludes | Lead Tester | Full Time |
| Mariae May Salpid | Tester | Full Time |
| Cherrylen Lingo Casimero | UX Design | Full Time |

Table 3 Staff and Person Involved in Project

3.1.3. Resource Acquisition Plan

For the project, all required hardware, software, and tools are already on hand. The project team will send a letter of request to the School Principal asking permission to be the client in order to acquire the requirements. The proposer will carry out unofficial interviews and compile all the data gathered.

3.1.4. Project Staffing Plan

No training for TSNHS Gateway Monitoring System, project participants will be needed. The project team composed of one-man team only but already well-trained and has years of experience in an agile way of working.

  - Work Plan

This section provides a detailed breakdown of the TSNHS Gateway Monitoring System, project overall scope of work that the project team must complete to achieve the project goals and provides the necessary deliverables.

| Project Task |  | Estimated Schedule |
| --- | --- | --- |
| 1 | Iteration 1 |  |
| 1.1 | MVC Architecture | January 5-6, 2023 |
| 1.2 | Login Security | January 7-8, 2023 |
| 1.3 | Dashboard | January 9-11, 2023 |
| 1.4 | Students’ Information | January 12-18, 2023 |
| 1.5 | Grade and Section | January 19-24, 2023 |
| 1.6 | Teachers’ Information | January 25-28, 2023 |
| 1.7 | Advisory | January 29 – 31 , 2023 |
| 1.8 | Daily Record | February 1-5, 2023 |
| 1.9 | Monthly Record | February 6-9, 2023 |
| 1.10 | Users | February 10-12, 2023 |
| 1.11 | RFID_StudentData | February 13-18, 2023 |
| 1.12 | Software Testing | February 19 - 28, 2023 |
| 2 | Iteration 2 |  |
| 2.1 | Iteration 1 Revisions | March 1-5, 2023 |
| 2.2 | Students’ Information | March 6-8, 2023 |
| 2.3 | Grade and Section | March 9-11, 2023 |
| 2.4 | Teachers’ Information | March 12-14,2023 |
| 2.5 | Advisory | March 15-17, 2023 |
| 2.6 | Daily Record | March 16-18, 2023 |
| 2.7 | Software Testing | March 19-24, 2023 |
| 3 | Iteration 3 |  |
| 3.1 | Iteration 1 and 2 Revisions | March 25-28, 2023 |
| 3.2 | Software Testing | March 29 – April 3, 2023 |

Table 4 Work Plan

    - Work Activities

The table of work activities list the various chores for each iteration. The total person assigned to the assignment is also displayed, along with the number of hours allotted for each activity.

| Project Task |  | Role | Labor Hours |
| --- | --- | --- | --- |
| 1 | Iteration 1 |  |  |
| 1.1 | MVC Architecture |  | 40 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 8 |
|  | MVC Structure Development | Developer | 20 |
|  | Software Test | Lead Tester | 10 |
| 1.2 | Login Security |  | 18 |
|  | Kick-off Meeting | Project Manager | 1 |
|  | Requirements Gathering | Project Manager | 2 |
|  | Database Design | Developer | 3 |
|  | User Interface Design | Developer | 4 |
|  | Login Development | Developer | 6 |
|  | Software Test | Lead Tester | 2 |
| 1.3 | Dashboard |  | 13 |
|  | Kick-off Meeting | Project Manager | 4 |
|  | Database Design | Developer | 2 |
|  | User Interface Design | Developer | 4 |
|  | Software Test | Lead Tester | 3 |
| 1.4 | Students’ Information |  | 35 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 2 |
|  | Database Design | Developer | 3 |
|  | User Interface Design | Developer | 5 |
|  | CRUD Operation | Developer | 8 |
|  | Software Test | Lead Tester | 15 |
| 1.5 | Grade and Section |  | 70 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 2 |
|  | Database Design | Developer | 3 |
|  | User Interface Design | Developer | 5 |
|  | CRUD Operation | Developer | 15 |
|  | Software Test | Lead Tester | 25 |
| 1.6 | Teachers’ Information |  | 58 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 3 |
|  | Database Design | Developer | 8 |
|  | User Interface Design | Developer | 15 |
|  | CRUD Operation | Developer | 15 |
|  | Software Test | Lead Tester | 15 |
| 1.7 | Advisory |  | 36 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 5 |
|  | Database Design | Developer | 4 |
|  | User Interface Design | Developer | 5 |
|  | Retrieved | Developer | 15 |
|  | Software Test | Lead Tester | 5 |
| 1.8 | Daily Record |  | 56 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 10 |
|  | Database Design | Developer | 10 |
|  | User Interface Design | Developer | 10 |
|  | Retrieved | Developer | 15 |
|  | Software Test | Lead Tester | 10 |
| 1.9 | Monthly Record |  | 56 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 10 |
|  | Database Design | Developer | 10 |
|  | User Interface Design | Developer | 10 |
|  | Retrieved | Developer | 15 |
|  | Software Test | Lead Tester | 10 |
| 1.10 | Users |  | 36 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 3 |
|  | Database Design | Developer | 3 |
|  | User Interface Design | Developer | 5 |
|  | Retrieved | Developer | 8 |
|  | Software Test | Lead Tester | 15 |
| 1.11 | RFID_StudentData |  | 63 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 4 |
|  | Database Design | Lead Developer | 3 |
|  | User Interface Design | Lead Developer | 4 |
|  | Retrieved | Lead Developer | 20 |
|  | Software Test | Lead Tester | 30 |
| 1.12 | Software Testing |  | 90 |
|  | Kick-off Meeting | Project Manager | 4 |
|  | Software Test | Lead Tester | 80 |
|  | Approval | Project Manager | 6 |
| 2 | Iteration 2 |  |  |
| 2.1 | Iteration 1 Revisions |  | 120 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Development Phase | Lead Developer | 100 |
|  | Software Test | Lead Tester | 18 |
| 2.2 | Students’ Information |  | 35 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 4 |
|  | Database Design | Lead Developer | 4 |
|  | User Interface Design | Lead Developer | 5 |
|  | CRUD Operation | Lead Developer | 10 |
|  | Software Test | Lead Tester | 10 |
| 2.3 | Grade and Section |  | 35 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 4 |
|  | Database Design | Lead Developer | 4 |
|  | User Interface Design | Lead Developer | 5 |
|  | CRUD Operation | Lead Developer | 10 |
|  | Software Test | Lead Tester | 10 |
| 2.4 | Advisory |  | 29 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 4 |
|  | User Interface Design | Lead Developer | 3 |
|  | Retrieved | Lead Developer | 10 |
|  | Software Test | Lead Tester | 10 |
| 2.4 | Daily Record |  | 29 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Requirements Gathering | Project Manager | 4 |
|  | Database Design | Lead Developer | 3 |
|  | User Interface Design | Lead Developer | 10 |
|  | Retrieved | Lead Developer | 10 |
|  | Software Test | Lead Tester | 29 |
| 2.5 | Software Testing |  | 32 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Software Test | Lead Tester | 28 |
|  | Approval | Project Manager | 2 |
| 3 | Iteration 3 |  |  |
| 3.1 | Iteration 1 and 2 Revisions |  | 74 |
|  | Kick-off Meeting | Project Manager | 2 |
|  | Development Phase | Lead Developer | 52 |
|  | Software Test | Lead Tester | 20 |
| 3.2 | Software Testing |  | 68 |
|  | Kick-off Meeting | Project Manager | 3 |
|  | Software Test | Lead Tester | 60 |
|  | Approval | Project Manager | 5 |

Table 5 Work Activities

3.2.2. Schedule Allocation

The project can only go through three iterations in total. Each iteration is given a different number of working hours since each has a different set of responsibilities. The timetable provided, nevertheless, could change in reaction to modifications in the user's needs.

    - Resource Allocation

The development team for the project has a specific amount of time given to it. The entire development process takes three iterations. The development team is allowed 350 hours for the first iteration, 328 hours for the second, and 152 hours for the third to complete the demands and responsibilities assigned to them.

    - Budget Allocation

During the development phase, no budget was paid by stakeholders. As a result, there is no need for a budget allocation strategy.

  - Control Plan

    - Requirements Control Plan

Requirement will be managed in use case description of SRS as requirements are changed.

    - Schedule Control Plan

A daily stand-up meeting will be held by the development team to assess daily progress. The meeting would be supervised with the project manager. Each team member must describe their current status, any obstacles they are facing, and the goal they want to complete the following day. As a result, everyone on the team is aware of each developer’s position. They can also gain knowledge about the many obstacles that the other developer has stated. The development team will also hold a retrospective meeting to assess whether the team produced quality work for the most recent iteration. The practices that need to be changed are then identified to improve the performance of the team.

    - Budget Control Plan

As stated under section 3.2 sub section 3.2.3, no budget was provided for the development of the project.

    - Quality Control Plan

A unique software testing document will be produced by the tester. Checklist and other evaluation techniques will be found to be required or not based on this guideline. The development team’s primary quality control tools for the work process and final product will be unit testing. A more comprehensive plan is shown at the software testing plan.

    - Reporting Plan

All the conclusion of each iteration, the team will deliver a report to the user. This is an update on how development is coming along. The team will meet every day while it is being developed to give an update on the task that have been completed.

    - Metrics Collection Plan

Daily stand-up meetings will be held, as specified in the schedule control plan, to monitor the advancement and obstacles of each member. Additionally, a meeting for reflection is held after iteration.

    - Risk Management Plan

Each step will begin with the identification of risk, which the team lead well then compile into a list of prioritized hazards. The team members will discuss risks and reassess then prioritized risks at the daily stand-up meeting. All risks and tasks that need to be accomplished will be identified, and team members will decide on mitigation strategies before assigning these risks and duties as action item. Every week, the team will check on high priority hazards.

    - Project Closeout Plan

The development team will ensure the proper closeout of the project in the second semester of the academic year 2022-2023.

- Technical Process Plans

  - Process Model

A framework or approach for agile project management that is primarily utilized in software development projects with the objective of delivering new software capability. The project methodology includes iteration. Regular iteration reviews once a week to present the work performed and the daily meeting for updates, which is the deciding components.

  - Methods, Tools, and Technique

The methods and techniques listed in the table will be evaluated and applied in specific areas of the project as appropriate:

| Category | Methods and Techniques |
| --- | --- |
| Requirements Elicitation | Meetings, Interviews, Brainstorming |
| Formal Specification and Analysis | Formal models using UML to model structural aspects of the requirements and design Use cases to define requirements |
| Prototype | Draw.io Application |

Table 6 Methods and Techniques

| Category | Tools |
| --- | --- |
| Operating System | Windows 10 Pro |
| Programming Language | Hypertext Preprocessor |
| Database | MySQL |
| Front-end Design | Bootstrap Framework |
| Diagrams | Draw.io Application |
| Documents | All documents will be written using Microsoft Word |

Table 7 Tools

  - Infrastructure Plan

No infrastructure plan is defined in this project.

  - Product Acceptance Plan

Representative from the clients will be presented with Project Acceptance Form wherein the in-charge personnel of the proposed project will sign as a proof of accepting the final project.

- Supporting Process Plans

  - Verification and Validation Plan

The development team has created a separate Software Testing Document for the verification and validation.

  - Documentation Plan

There are number of documents that will be produced during the lifetime of the project. All documents are responsibility of the project team members. The lists of documents that will be created and maintained under version control include:

- Software Project Management Plan (SPMP)

- Software Requirements Specification (SRS)

- Software Design Description (SDD)

- Software Testing Document (STD)

  - Quality Assurance Plan

To ensure the quality of product, results from software test document shall be evaluated to distinguish all problems encountered. Problems found shall be fixed then.

  - Problem Resolution Plan

Any major problem encountered by the development team should be discussed during the scheduled meeting. Decisions are to be finalized by the project manager.